## About
Created on: | 29 May 23 12:36 UTC
Jira Site: | https://honchoworks.atlassian.net
Jira Query: | issueKey in (FW-389, FW-752, FW-2560, FW-2687, FW-2697, FW-2698, FW-2801, FW-2814, FW-2863, FW-2882, FW-2886, FW-2899, FW-2909, FW-2920, FW-2947, FW-2953, FW-2954, FW-2955, FW-2956, FW-2966, FW-2969, FW-2971, FW-2974, FW-2980, FW-2987, FW-2988, FW-2990, FW-301, FW-309, FW-390, FW-2688, FW-2690, FW-2755, FW-2831, FW-2893, FW-2898, FW-2904, FW-2918, FW-2939, FW-2940, FW-2945, FW-2946, FW-2952, FW-2972, FW-2973, FW-2979, FW-2991) ORDER BY status DESC

## Your Jira Issues
Issue Type | Key | Summary | Assignee | Priority | Status | Resolution | Created | Updated | Due date | Labels | Sprint | Story Points
Story | FW-2687 | View Alert Details related to IM | Edwin Deliz | Medium | QA-Prod |  | 2023-01-05 11:26 | 2023-05-29 05:35 |  | C.QOL;P.Review | Sprint 50;Sprint 51;Sprint 52 | 6
Support | FW-2987 | Guide install via .ps1 - PBF | Sean Sullivan | Medium | UAT |  | 2023-05-22 06:57 | 2023-05-29 05:35 |  | P.Guide;unplanned | Sprint 51;Sprint 52 | 3
Bug | FW-2956 | BCC recipients not showing in Alert details | Sean Sullivan | High | UAT |  | 2023-05-02 12:08 | 2023-05-29 05:35 |  | P.Review | Sprint 51;Sprint 52 | 2
Story | FW-2980 | baseline automated test for inbox that makes sure it loads and shows a few emails | Giorgio Catenacci | Medium | RTD Staging |  | 2023-05-15 12:18 | 2023-05-29 05:35 |  | unplanned | Sprint 51;Sprint 52
Bug | FW-2971 | Mapped communication sources are not working | Giorgio Catenacci | Medium | RTD Staging |  | 2023-05-04 13:10 | 2023-05-29 05:35 |  | P.Review | Sprint 51;Sprint 52 | 2
Story | FW-2909 | Message Attachment ETL | Giorgio Catenacci | Medium | Review |  | 2023-04-12 09:08 | 2023-05-29 05:35 |  |  | Sprint 50;Sprint 51;Sprint 52 | 3
Support | FW-2801 | MOT - Reparsing of ICE chat data from Jan. 20 - Feb 9th | Giorgio Catenacci | Medium | Review |  | 2023-02-15 09:41 | 2023-05-29 05:35 |  |  | FW Sprint 45;FW Sprint 46;FW Sprint 47;FW Sprint 48;FW Sprint 49;Sprint 50;Sprint 51;Sprint 52 | 4
Story | FW-2697 | Manually manage list of senders to ignore | Egor Voronin | Medium | Review |  | 2023-01-05 12:37 | 2023-05-29 05:35 |  |  | Sprint 51;Sprint 52 | 4
Bug | FW-389 | Glencore: OCSP Stapling Not Configured on Server | Giorgio Catenacci | Low | Blocked |  | 2021-06-14 09:00 | 2023-05-29 05:35 |  | C.GLE;security | HON Sprint 15;FW Sprint 16;FW Sprint 17;Sprint 51;Sprint 52 | 2
Incident | FW-2991 | GNV SSO login has stopped redirecting to the Azure sign-in page. | Paul Barrick | Critical | Done |  | 2023-05-23 09:45 | 2023-05-25 11:25 |  |  | Sprint 51
Incident | FW-2979 | Server error message displays in CID | Giorgio Catenacci | Critical | Done |  | 2023-05-15 12:14 | 2023-05-15 15:58 |  |  | Sprint 51
Bug | FW-2973 | CWToKafka lambda got econtimeout/reset when trying to send a lot of logs | Sean Sullivan | Medium | Done |  | 2023-05-08 04:20 | 2023-05-23 12:10 |  |  | Sprint 50;Sprint 51 | 1
Bug | FW-2972 | Unable to create more than 1 mapped per source account | Sean Sullivan | Medium | Done |  | 2023-05-04 13:10 | 2023-05-23 12:10 |  | P.Review | Sprint 51 | 2
Story | FW-2952 | Review Inbox - Filter by Keyword | Sean Sullivan | Medium | Done |  | 2023-05-01 13:37 | 2023-05-19 12:28 |  | P.Review | Sprint 50;Sprint 51 | 3
Bug | FW-2946 | Showing the wrong username at times in Alerts | Sean Sullivan | Medium | Done |  | 2023-04-28 07:09 | 2023-05-19 12:28 |  | P.Review | FW Sprint 49;Sprint 50;Sprint 51 | 2
Support | FW-2945 | GLE - Setting up Kibana DIP dashboard in CMPC environment | Giorgio Catenacci | Medium | Done |  | 2023-04-27 13:08 | 2023-05-23 07:03 |  |  | Sprint 50;Sprint 51 | 2
Bug | FW-2940 | Review Inbox filtering - functional issues | Sean Sullivan | High | Done |  | 2023-04-25 08:30 | 2023-05-19 12:28 |  | P.Review | Sprint 50;Sprint 51 | 2
Bug | FW-2939 | Review Inbox filtering - style issues | Sean Sullivan | Medium | Done |  | 2023-04-25 08:30 | 2023-05-19 12:28 |  | P.Review | Sprint 50;Sprint 51 | 1
Support | FW-2918 | PBF - Teams Implementation | Giorgio Catenacci | Medium | Done |  | 2023-04-14 07:23 | 2023-05-19 02:07 |  |  | Sprint 50;Sprint 51 | 3
Story | FW-2904 | View Closed Alert List and Filter | Sean Sullivan | Medium | Done |  | 2023-04-10 16:46 | 2023-05-17 10:51 |  |  | FW Sprint 49;Sprint 50;Sprint 51 | 4
Task | FW-2898 | CloudWatch consumer to add field about the environment from which the log is coming | Sean Sullivan | Medium | Done |  | 2023-04-06 01:42 | 2023-05-23 07:03 |  |  | Sprint 50;Sprint 51 | 2
Story | FW-2893 | User-friendly, account unique IDs for alerts and messages | Sean Sullivan | Medium | Done |  | 2023-03-31 14:10 | 2023-05-24 13:14 |  |  | FW Sprint 49;Sprint 50;Sprint 51 | 2
DevOps | FW-2831 | Prod vpn new configuration does not work | Giorgio Catenacci | Medium | Done |  | 2023-03-03 04:31 | 2023-05-18 08:29 |  |  | FW Sprint 46;FW Sprint 47;FW Sprint 48;FW Sprint 49;Sprint 50;Sprint 51 | 2
Story | FW-2755 | Alert Inbox sorting | Sean Sullivan | Medium | Done |  | 2023-01-27 05:55 | 2023-05-17 10:43 |  |  | Sprint 50;Sprint 51 | 4
Story | FW-2690 | Assign User to alert | Sean Sullivan | Medium | Done |  | 2023-01-05 11:33 | 2023-05-17 10:56 |  |  | FW Sprint 49;Sprint 50;Sprint 51 | 2
Story | FW-2688 | Highlight Flagged Text in Alerts | Sean Sullivan | Medium | Done |  | 2023-01-05 11:29 | 2023-05-17 10:58 |  |  | Sprint 50;Sprint 51 | 3
Bug | FW-390 | Glencore: Insecure TLS Configuration | Paul Barrick | Low | Done |  | 2021-06-14 09:00 | 2023-05-29 05:18 |  | C.GLE;security | Sprint 51 | 6
Task | FW-309 | Pensive: Outdated TLS Versions Supported; CVSS Total: 5.5 | Paul Barrick | Medium | Done |  | 2021-05-18 08:52 | 2023-05-29 05:17 |  | AuthServer;CID;EMD;RA;security | Sprint 51 | 6
Task | FW-301 | Pensive: CORS Header Misconfiguration; CVSS 8.5 | Paul Barrick | Medium | Done |  | 2021-05-18 08:24 | 2023-05-29 05:09 |  | RA;security | HON Sprint 11;HON Sprint 12;HON Sprint 13;HON Sprint 14;HON Sprint 15;FW Sprint 16;FW Sprint 17;Sprint 51;HON Sprint 10 | 2
Story | FW-2954 | IM Alert Details - indicate alerted context msgs | Edwin Deliz | Medium | QA |  | 2023-05-02 09:04 | 2023-05-29 05:35 |  | C.QOL;P.Review | Sprint 51;Sprint 52 | 3
Story | FW-2953 | Decorate IM Alert with Context Messages | Edwin Deliz | Medium | QA |  | 2023-05-02 08:42 | 2023-05-29 05:35 |  | P.Review | Sprint 50;Sprint 51;Sprint 52 | 2
Story | FW-2947 | ETL Handle Duplicate Messages | Edwin Deliz | Medium | QA |  | 2023-04-28 07:30 | 2023-05-29 05:35 |  | P.Review | Sprint 50;Sprint 51;Sprint 52 | 2
Story | FW-2920 | Create TeamsH pipeline for ETL | Edwin Deliz | Medium | QA |  | 2023-04-17 08:37 | 2023-05-29 05:35 |  | P.Review | FW Sprint 49;Sprint 50;Sprint 51;Sprint 52 | 6
Story | FW-2698 | Do not analyze messages from "Ignore Senders" list | Edwin Deliz | Medium | QA |  | 2023-01-05 12:38 | 2023-05-29 05:35 |  |  | Sprint 51;Sprint 52 | 3
DevOps | FW-2560 | Finish automation for TGP cypress fix | Paul Barrick | Medium | QA |  | 2022-12-02 09:07 | 2023-05-29 05:35 |  |  | FW Sprint 42;FW Sprint 43;FW Sprint 44;FW Sprint 45;FW Sprint 46;FW Sprint 47;FW Sprint 48;FW Sprint 49;Sprint 50;Sprint 51;Sprint 52 | 3
Incident | FW-2988 | [PRODUCTION DIP ERROR] - [parsers/teamsH] - processZippedMessages | Vladyslav Boiko | Medium | In Progress |  | 2023-05-22 08:43 | 2023-05-29 05:35 |  | P.R&A;unplanned | Sprint 51;Sprint 52
Task | FW-2974 | Review Testing Setup | Edwin Deliz | Medium | In Progress |  | 2023-05-09 09:02 | 2023-05-29 05:35 |  |  | Sprint 50;Sprint 51;Sprint 52 | 3
DevOps | FW-2969 | Improve jenkins pipeline for ETL | Giorgio Catenacci | High | In Progress |  | 2023-05-04 01:09 | 2023-05-29 05:35 |  | P.Review | Sprint 50;Sprint 51;Sprint 52 | 2
Story | FW-2955 | IM Alert Details - aggregate context participants and flags to header | Egor Voronin | Medium | In Progress |  | 2023-05-02 09:04 | 2023-05-29 05:35 |  | C.QOL;P.Review | Sprint 51;Sprint 52 | 4
Story | FW-2899 | Message Attachments viewable inside Alerts | Egor Voronin | Medium | In Progress |  | 2023-04-07 11:45 | 2023-05-29 05:35 |  |  | Sprint 50;Sprint 51;Sprint 52 | 2
DevOps | FW-2863 | Fix ES Sync Job | Subho Das | Medium | In Progress |  | 2023-03-16 07:15 | 2023-05-29 05:35 |  |  | FW Sprint 48;FW Sprint 49;Sprint 50;Sprint 51;Sprint 52 | 3
DevOps | FW-2814 | CID in ECS is not sending logs to CloudWatch | Subho Das | Medium | In Progress |  | 2023-02-27 00:02 | 2023-05-29 05:35 |  |  | FW Sprint 46;FW Sprint 47;FW Sprint 48;FW Sprint 49;Sprint 50;Sprint 51;Sprint 52 | 3
DevOps | FW-2990 | Teams batch import on cron base from Jenkins pipeline into ETL | Giorgio Catenacci | Medium | Refine |  | 2023-05-23 03:15 | 2023-05-29 05:35 |  | P.Review;unplanned | Sprint 51;Sprint 52
DevOps | FW-2966 | [Vanta] Remediate "Medium vulnerabilities identified on EC2 instances are addressed (AWS Inspector)" | Giorgio Catenacci | Medium | Refine |  | 2023-05-03 10:30 | 2023-05-29 05:35 |  | vanta | Sprint 51;Sprint 52
DevOps | FW-2886 | Guide environment should be spun up on creation of release branch | Giorgio Catenacci | Medium | Refine |  | 2023-03-30 09:18 | 2023-05-29 05:35 |  | unplanned | Sprint 51;Sprint 52
DevOps | FW-2882 | Create ephemeral domains | Giorgio Catenacci | Medium | Refine |  | 2023-03-30 09:16 | 2023-05-29 05:35 |  | unplanned | Sprint 51;Sprint 52
Bug | FW-752 | Internal: RA API ACL allows authorized users create and update entities in our database | Giorgio Catenacci | Medium | Refine |  | 2021-06-14 16:43 | 2023-05-29 05:35 |  | RA;security | Sprint 51;Sprint 52