## About
Created on: | 28 Jun 23 15:32 UTC
Jira Site: | https://honchoworks.atlassian.net
Jira Query: | issueKey in (FW-389,FW-752,FW-2689,FW-2696,FW-2756,FW-2801,FW-2814,FW-2839,FW-2864,FW-2913,FW-2984,FW-2990,FW-2998,FW-3013,FW-3024,FW-3030,FW-3035,FW-3039,FW-3043,FW-3047,FW-3050,FW-3070,FW-3072, FW-2917,FW-2982,FW-2996,FW-3000,FW-3001,FW-3020,FW-3025,FW-3036,FW-3038,FW-3040,FW-3045)

## Your Jira Issues
Issue Type | Key | Summary | Assignee | Priority | Status | Resolution | Created | Updated | Due date | Labels | Sprint | Story Points
Incident | FW-3072 | TOT user unable to escalate message | Egor Voronin | Critical | In Progress |  | 2023-06-27 07:35 | 2023-06-28 03:11 |  |  | Sprint 53;Sprint 54
Incident | FW-3070 | MER VPN expired | Subho Das | Critical | Refine |  | 2023-06-26 10:38 | 2023-06-27 22:57 |  |  | Sprint 53;Sprint 54
Task | FW-3050 | Guide backend response for Bragi must contain ITBs | Sean Sullivan | Medium | UAT-Prod |  | 2023-06-20 05:48 | 2023-06-28 08:09 |  | P.Review | Sprint 53;Sprint 54 | 1
Story | FW-3047 | Review Inbox is too cramped - needs more spacing | Edwin Deliz | Medium | QA-Prod |  | 2023-06-14 14:28 | 2023-06-28 06:48 |  | P.Review | Sprint 53;Sprint 54 | 1
Spike | FW-3045 | Research and Document conclusions on how we plan to architect Retention & Purging for Review / Keep | Paul Barrick | Medium | Done |  | 2023-06-13 11:12 | 2023-06-27 11:51 |  |  | Sprint 53 | 3
Story | FW-3043 | Review Inbox Frontend - filter by message participants | Ken Cruz | Medium | Review |  | 2023-06-13 11:04 | 2023-06-28 03:07 |  | P.Review | Sprint 53;Sprint 54 | 3
Task | FW-3040 | Create a shared code library from Bragi utils and reuse it in ETL | Giorgio Catenacci | Medium | Done |  | 2023-06-13 06:10 | 2023-06-26 03:39 |  | Bragi;ETL;P.Review | Sprint 53 | 2
DevOps | FW-3039 | Create a Jenkins job to clear MER Batch queue | Subho Das | Medium | In Progress |  | 2023-06-13 01:50 | 2023-06-27 22:57 |  |  | Sprint 53;Sprint 54 | 3
Spike | FW-3038 | Investigate why some emails are going to error folder | Giorgio Catenacci | Medium | Done |  | 2023-06-12 07:01 | 2023-06-20 06:01 |  |  | Sprint 53 | 3
Spike | FW-3036 | Emails to Frank Strouds sent to REV and not TRD as expected | Vladyslav Boiko | Medium | Done |  | 2023-06-09 08:39 | 2023-06-20 01:57 |  | P.Review | Sprint 53 | 2
Spike | FW-3035 | Two accounts have FAI as their initials | Paul Barrick | Medium | Review |  | 2023-06-09 08:23 | 2023-06-27 22:57 |  |  | Sprint 53;Sprint 54 | 3
Task | FW-3030 | Configure retry policy for email parser | Giorgio Catenacci | Medium | RTD Staging |  | 2023-06-08 07:55 | 2023-06-27 22:57 |  |  | Sprint 53;Sprint 54 | 3
Task | FW-3025 | Unit tests for the shared code of ETL processors | Giorgio Catenacci | Medium | Done |  | 2023-06-06 07:29 | 2023-06-27 22:58 |  | ETL;P.Review | Sprint 52;Sprint 53 | 3
Task | FW-3024 | Create statistics service | Vladyslav Boiko | Medium | In Progress |  | 2023-06-06 05:22 | 2023-06-27 22:58 |  | P.Keep;P.Review | Sprint 53;Sprint 54 | 3
Task | FW-3020 | Unit tests for email parser ETL | Giorgio Catenacci | Medium | Done |  | 2023-06-02 05:32 | 2023-06-27 22:58 |  | P.Review | Sprint 52;Sprint 53 | 3
Task | FW-3013 | Update Bragi to use Kafka caching | Giorgio Catenacci | Medium | Refine |  | 2023-06-01 08:01 | 2023-06-27 22:57 |  | P.Review | Sprint 53;Sprint 54 | 5
Task | FW-3001 | Upgrade Cypress | Edwin Deliz | Medium | Done |  | 2023-05-29 05:56 | 2023-06-27 12:05 |  |  | Sprint 53 | 3
Spike | FW-3000 | 2998 Cert investigation spike | Paul Barrick | Medium | Done |  | 2023-05-29 05:47 | 2023-06-13 12:22 |  |  | Sprint 52;Sprint 53 | 2
DevOps | FW-2998 | SSL certificate for GC4 is expiring | Giorgio Catenacci | Medium | Refine |  | 2023-05-26 01:28 | 2023-06-27 22:57 |  |  | Sprint 53;Sprint 54 | 2
DevOps | FW-2996 | Schedule auth server to auto restart periodically (nightly?) | Giorgio Catenacci | Medium | Done |  | 2023-05-25 11:23 | 2023-06-15 05:04 |  | C.ATA;C.GNV;C.MOT;P.R&A;stability | Sprint 53 | 1
DevOps | FW-2990 | Teams batch import on cron base from Jenkins pipeline into ETL | Edwin Deliz | Medium | QA-Prod |  | 2023-05-23 03:15 | 2023-06-28 06:23 |  | P.Review | Sprint 51;Sprint 52;Sprint 53;Sprint 54 | 2
Task | FW-2984 | Kill BETM GC3 clients | Subho Das | Medium | In Progress |  | 2023-05-18 11:23 | 2023-06-27 22:57 |  |  | Sprint 53;Sprint 54 | 3
DevOps | FW-2982 | BB changes SSH and we do the same before 20 June | Giorgio Catenacci | Medium | Done |  | 2023-05-17 08:06 | 2023-06-14 08:17 |  |  | Sprint 52;Sprint 53 | 2
Bug | FW-2917 | MER email parser is getting access denied sometimes | Sean Sullivan | Medium | Done |  | 2023-04-14 05:23 | 2023-06-27 22:58 |  | P.R&A | Sprint 53
Story | FW-2913 | Fairwords Platform without Guide enabled | Sean Sullivan | Medium | UAT-Prod |  | 2023-04-12 15:32 | 2023-06-28 08:06 |  | P.Review | Sprint 53;Sprint 54 | 2
Story | FW-2864 | Quick actions in alert list | Edwin Deliz | Medium | QA-Prod |  | 2023-03-16 07:40 | 2023-06-28 06:32 |  | P.Review | Sprint 53;Sprint 54 | 4
Story | FW-2839 | Change Alert Status (bulk/list) | Edwin Deliz | Medium | QA-Prod |  | 2023-03-06 14:43 | 2023-06-28 06:32 |  | P.Review | Sprint 53;Sprint 54 | 3
DevOps | FW-2814 | CID in ECS is not sending logs to CloudWatch | Subho Das | Medium | Refine |  | 2023-02-27 00:02 | 2023-06-27 22:57 |  |  | FW Sprint 46;FW Sprint 47;FW Sprint 48;FW Sprint 49;Sprint 50;Sprint 51;Sprint 52;Sprint 53;Sprint 54 | 3
Support | FW-2801 | MOT - Reparsing of ICE chat data from Jan. 20 - Feb 9th | Edwin Deliz | Medium | QA-Prod |  | 2023-02-15 09:41 | 2023-06-28 06:54 |  |  | FW Sprint 45;FW Sprint 46;FW Sprint 47;FW Sprint 48;FW Sprint 49;Sprint 50;Sprint 51;Sprint 52;Sprint 53;Sprint 54 | 4
Story | FW-2756 | Review Inbox Backend - filter by message participants | Ken Cruz | Medium | Review |  | 2023-01-27 06:07 | 2023-06-28 03:08 |  | P.Review | Sprint 53;Sprint 54 | 3
Story | FW-2696 | Ignore text blocks from detection | Giorgio Catenacci | Medium | RTD Prod |  | 2023-01-05 12:26 | 2023-06-27 22:57 |  |  | Sprint 53;Sprint 54 | 5
Story | FW-2689 | Quickly Navigate to Flagged Text in Alerts | Egor Voronin | Medium | In Progress |  | 2023-01-05 11:30 | 2023-06-27 22:57 |  | P.Review | Sprint 53;Sprint 54 | 3
Bug | FW-752 | Internal: RA API ACL allows authorized users create and update entities in our database | Giorgio Catenacci | Medium | UAT |  | 2021-06-14 16:43 | 2023-06-27 22:57 |  | P.R&A;RA;security | Sprint 51;Sprint 52;Sprint 53;Sprint 54 | 2
Bug | FW-389 | Glencore: OCSP Stapling Not Configured on Server | Giorgio Catenacci | Low | Blocked |  | 2021-06-14 09:00 | 2023-06-27 22:57 |  | C.GLE;P.R&A;security | HON Sprint 15;FW Sprint 16;FW Sprint 17;Sprint 51;Sprint 52;Sprint 53;Sprint 54 | 2